## PROJECT CHARTER
PROJECT CHARTER
PROJECT NAME			PROJECT MANAGER		PROJECT SPONSOR
Development of a Class Website			Jane Matthews		Jill DeGrassio
EMAIL		PHONE	ORGANIZATIONAL UNIT(S)
jane.matthews@positivecharge.com		9086745645	Web Development, IT Operations, and Project Management
GREEN BELTS ASSIGNED			EXPECTED START DATE		EXPECTED COMPLETION DATE
Wendy Williams (Web Development)			22/01/2025		25/07/2025
BLACK BELTS ASSIGNED			EXPECTED SAVINGS		ESTIMATED COSTS
Rakesh Agarwal (Director of IT Operations)			$15,000.00		$250,000.00

PROJECT OVERVIEW
PROBLEM OR ISSUE	The goal of this project is to develop a custom class website with features such as a home page, syllabus page, student and teacher login portals, and other relevant sections to improve communication and learning management.
PURPOSE OF PROJECT	The implementation of this custom class website will enhance the educational experience by providing a centralized platform for students and teachers to access critical resources. It aims to simplify communication, facilitate efficient information sharing, and promote user-friendly engagement.
BUSINESS CASE	Educational institutions are increasingly relying on digital platforms to improve teaching and learning. A custom-built class website will cater to specific class needs, ensure a unique identity, and avoid dependency on third-party solutions. This initiative will provide a streamlined user experience for students and teachers and reduce administrative overhead.
GOALS / METRICS	The project goal is to design and implement a fully functional class website by the target date. Metrics for success include meeting deadlines, maintaining website uptime of 99%, achieving a 95% satisfaction rate in user feedback, and ensuring compatibility with all major devices and browsers.
EXPECTED DELIVERABLES	- A responsive class website with: / 1. Home page / 2. Syllabus page / 3. Student login portal / 4. Teacher login portal / 5. Announcements and updates section / 6. Contact and helpdesk page / - Documentation for website management and maintenance.

PROJECT SCOPE
WITHIN SCOPE	Design and development of a custom website template. / Integration of login portals for students and teachers. / Development of a content management system for syllabus and announcements. / User testing and feedback incorporation. / Providing training for teachers to manage the website content.
OUTSIDE OF SCOPE	Hosting and domain registration (to be handled by the institution). / Third-party API integrations for external learning tools. / Maintenance and updates post-deployment.

TENTATIVE SCHEDULE
KEY MILESTONE			START		FINISH
Form Project Team / Preliminary Review / Scope			22/01/2025		31/01/2025
Finalize Project Plan / Charter / Kick Off			01/02/2025		15/02/2025
Define Phase			16/02/2025		28/02/2025
UI/UX Design Phase			01/03/2025		15/03/2025
Backend Development			16/03/2025		15/05/2025
Frontend Integration			16/05/2025		15/06/2025
Testing Phase			16/06/2025		10/07/2025
Project Summary Report and Close Out			11/07/2025		25/07/2025

RESOURCES
PROJECT TEAM	Janine Remagio		Project Manager
	David Coen		Lead Developer
	Rita Preze		UI/UX Designer
	Lisa Jones		QA Specialist
	Donald Smythe		Frontend Developer
SUPPORT RESOURCES	IT Operations, Sales, and Web Development Team
SPECIAL NEEDS	Access to existing class data, user feedback, and testing environments.

COSTS
COST TYPE	VENDOR / LABOR NAMES		AMOUNT
Labor	Lead Developer		$150,000.00
Labor	UI/UX Designer		$70,000.00
Labor	QA Specialist		$25,000.00
Miscellaneous	Third-Party Software		$5,000.00
	TOTAL COSTS		$250,000.00

BENEFITS AND CUSTOMERS
PROCESS OWNER	Jane Matthews - Project Manager
KEY STAKEHOLDERS	Jill DeGrassio, Teachers, Students
FINAL CUSTOMER	Students and teachers utilizing the class website.
EXPECTED BENEFITS	The class website will streamline communication between students and teachers, reduce administrative tasks, and provide a professional and engaging user experience. It will also facilitate efficient syllabus and announcement sharing, enhancing overall satisfaction.

TYPE OF BENEFIT	BASIS OF ESTIMATE				ESTIMATED BENEFIT AMOUNT
Improved Communication	IT and Management Estimations				$10,000.00
Enhanced User Satisfaction	User Surveys				$8,000.00
Reduced Administrative Work	Operations' Estimations				$5,000.00
Cost Savings on Third-Party	Software Estimations				$2,000.00
TOTAL BENEFIT					$25,000.00

RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS	- Delays in obtaining feedback from students and teachers during the testing phase. / - Potential compatibility issues with older devices and browsers. / - Limited access to IT resources during peak institutional periods.
CONSTRAINTS	- Project timeline is tight due to the academic calendar. / - Team members may need to multitask with other institutional IT priorities.
ASSUMPTIONS	- Necessary approvals from stakeholders will be obtained on time. / - Required class data and content for the website will be provided promptly.

PREPARED BY	TITLE				DATE
Jane Matthews	Senior Project Manager				21/01/2025

## PROJECT MANAGEMENT PLAN
PROJECT MANAGEMENT PLAN
OVERVIEW
Purpose	Develop a class website including home page, syllabus, student and teacher login portals.
Scope	Comprehensive design, secure login, usability focus.
Objective	Deliver within 6 months, $250,000 budget.
Assumptions	Content provided by stakeholders.
Constraints	Timeline and budget limitations, cross-browser/device compatibility.
Project Deliverables	Fully functional class website, documentation, secure portals for students and teachers.
Schedule	Start Date: January 22, 2025,	End Date: July 25, 2025,
Budget	$250,000.00
Evolution of the Plan	Plan updated at each milestone for scope, schedule, and resources.

PROJECT ORGANIZATION
External Interfaces	Coordinate with educators and students; IT for infrastructure support.
Internal Structure	Roles	Responsibility
	Project Manager	Oversee project lifecycle, monitor progress, and manage risks.
	Web Developers	Design, code, and implement website functionality.
	UI/UX Designer	Develop wireframes, design mockups, and ensure responsive design.
	Backend Developer	Set up database, develop authentication, and integrate backend logic.
	Frontend Developer	Implement front-end components, including portals and pages.
	QA Specialist	Conduct functionality, security, and usability testing.
	System Administrator	Deploy and manage the server and infrastructure.
Roles and Responsibilities	Assign roles and responsibilities to team members, ensuring clear ownership of tasks.

MANAGERIAL PROCESS PLAN
Start-Up Plans	Conduct resource estimation and plan staffing. / Acquire required tools and technologies. / Provide training on CMS, security protocols, and responsive design.
Work Plan	Phase 1: Requirements Gathering & Planning / Phase 2: UI/UX Design / Phase 3: Backend & Frontend Development / Phase 4: Integration & Testing / Phase 5: Deployment & Training
Control Plan	Conduct weekly progress meetings to track progress and address deviations. / Monitor deliverables and adjust timelines if required. / Regularly update the project charter and Gantt chart.
Risk Management Plan	Identified Risks: / Delays in stakeholder feedback. / Compatibility issues across devices. / Resource unavailability during critical phases. / Mitigation Strategies: / Maintain buffer time for feedback loops. / Conduct cross-device testing during development. / Pre-schedule resource availability.
Closeout Plan	Finalize website functionalities and documentation. / Conduct user training and collect feedback. / Conduct a retrospective to document lessons learned.

TECHNICAL PROCESS PLAN
Process Model	Follow Agile model for iterative development and progress tracking.
Methods, Tools, and Techniques	Tools	HTML, CSS, JavaScript for frontend. / CMS for content management. / Git for version control.
	Techniques	Responsive design for multi-device compatibility. / Usability optimization and secure login.
Infrastructure Plan	Hosting Services: Set up a secure hosting environment with backups. / Security: Implement SSL certificates and access control mechanisms.
Product Acceptance Plan	Conduct user testing with students and teachers. / Validate functionality against acceptance criteria. / Obtain formal acceptance from key stakeholders.

SUPPORTING PROCESS PLAN
Configuration Management Plan	Version control using Git for source code management.
Verification and Validation Plan	Functional, performance, and user acceptance testing.
Documentation Plan	User manuals and technical documentation.
Quality Assurance Plan	Adhere to quality standards through code reviews and QA processes.
Reviews and Audits	Bi-weekly reviews with stakeholders to ensure alignment.
Problem Resolution Plan	Log and resolve issues efficiently using an issue tracker.
Subcontractor Management Plan	No subcontractors planned for this project.
Process Improvement Plan	Integrate feedback continuously for process improvement.

## REQUIREMENT MATRIX
REQUIREMENT TRACEABILITY MATRIX (RTM)
PROJECT NAME: Class Website Development
DATE: March 31, 2025
Prepared By: Harshad Dhokane
Requirement Traceability Matrix (RTM)

Requirement ID	Requirement Description	Category	Source/Stakeholder	Priority	WBS Code	Deliverable	Verification Method
R1	Define project scope and requirements	Business Requirement	Project Manager, Educators	High	1.1	Approved Scope Document	Stakeholder Approval
R2	Identify key stakeholders and gather inputs	Business Requirement	Project Manager	High	1.1.1	Stakeholder Input Report	Meeting Records
R3	Define functional and non-functional specs	Functional Requirement	Educators, Students	High	1.1.2	Functional Requirements Document	Review and Sign-Off
R4	Create wireframes for website layout	UI/UX Design	UI/UX Designer	Medium	1.2.1	Initial Wireframes	UI/UX Review
R5	Develop UI mockups for all pages	UI/UX Design	UI/UX Designer	Medium	1.2.2	Final Visual Designs	Design Approval
R6	Set up the database and relationships	Technical	Database Administrator	High	1.3.1	Database Schema Design	Database Review
R7	Develop student and teacher authentication	Technical	Backend Developer	High	1.3.2	Secure Authentication System	Unit Testing
R8	Code and implement homepage layout	Development	Frontend Developer	High	1.4.1	Homepage Implementation	Code Review
R9	Develop student login and dashboard	Development	Frontend Developer	High	1.4.2	Student Portal Implementation	Functional Testing
R10	Conduct functional and performance testing	Quality Assurance	QA Team	High	1.5.1	Test Report	Test Case Results
R11	Deploy the website to a secure server	Deployment	System Administrator	High	1.5.2	Live Website Deployment	Deployment Verification
R12	Create user manuals and technical documentation	Documentation	Project Manager	Medium	1.6	User Manual and Admin Guide	Documentation Review
R13	Obtain feedback from users and incorporate improvements	User Feedback	Students, Teachers	Medium	1.7	Feedback Report	Survey Analysis
R14	Provide training for managing website content	Training	Project Manager, IT	Medium	1.8	Training Sessions and Guides	Training Feedback

Traceability Mapping Summary:

High Priority: Critical functionality including scope definition, authentication, homepage, portals, and database setup.
Medium Priority: UI/UX wireframes, documentation, feedback collection, and content management training.

Verification and Validation Methods
Stakeholder Approval: Scope documents and functional requirements sign-off.
UI/UX Reviews: Visual design and wireframe validation.
Code Reviews: Verify backend and frontend implementation.
Testing: Unit testing, functional testing, and performance validation.
Training Feedback: Evaluation from training sessions to ensure knowledge transfer.

Prepared By:
Harshad Dhokane
Senior Project Manager
Date: 31/03/2025

## SCOPE STATEMENT
PROJECT SCOPE STATEMENT FOR CLASS WEBSITE DEVELOPMENT
PROJECT NAME	CLASS WEBSITE DEVELOPMENT
DATE	March 31, 2025
PREPARED BY	HARSHAD DHOKANE

PROJECT SCOPE STATEMENT

PROJECT OBJECTIVE	The objective of this project is to design, develop, and deploy a fully functional class website that includes a home page, syllabus page, student and teacher login portals, announcements section, and contact/helpdesk page. The project will be completed within 3 months and within the allocated budget of $50,000.00.

PROJECT SCOPE DESCRIPTION	The class website will: / Include essential features: / Homepage with key information. / Syllabus page displaying course outlines and updates. / Secure student and teacher login portals. / Announcement and updates section to inform users of changes. / Contact/helpdesk page for queries and technical support. / Offer an intuitive UI/UX design for ease of use. / Ensure compatibility across multiple devices and browsers. / Implement secure authentication mechanisms to protect user data.

DELIVERABLES	The following deliverables will be produced: / Fully functional, responsive class website. / Secure login portals for students and teachers. / UI/UX wireframes and mockups. / Database for managing website content and user data. / User and technical documentation for website management. / Training sessions and guides for content management.

IN-SCOPE ITEMS	Design and Development:	UI/UX wireframes and interface designs. / Frontend and backend development. / Integration of login and content management system.
	Testing and Deployment:	Functional, performance, and security testing. / Hosting and deployment on a secure server.
	Documentation and Training:	Creation of user manuals and training resources. / Conducting training sessions for educators to manage content.

OUT-OF-SCOPE ITEMS	Hosting and Domain Registration: Institution is responsible for acquiring the domain and hosting. / Third-party Integrations: External learning tools and APIs are not included. / Ongoing Maintenance and Updates: Post-deployment support is not part of this phase.

PROJECT TIMELINE	Phase	Start Date	End Date
	Planning & Requirements	31/03/2025	07/04/2025
	UI/UX Design	08/04/2025	21/04/2025
	Backend Development	22/04/2025	12/05/2025
	Frontend Development	13/05/2025	28/05/2025
	Testing & Debugging	29/05/2025	07/06/2025
	Final Deployment & Training	08/06/2025	15/06/2025

ESTIMATED COST	The project is expected to be delivered within a budget of: $50,000.00

RISKS AND CONSTRAINTS	Risks:	Delays in stakeholder feedback during testing. / Technical challenges with ensuring multi-device compatibility. / Resource unavailability due to competing institutional priorities.
	Constraints:	Strict timeline due to academic schedule. / Budgetary limits and availability of key team members.

ASSUMPTIONS	Necessary approvals and feedback will be provided on time. / Content (syllabus, announcements) will be delivered by stakeholders. / IT infrastructure will be available for deployment and security testing.

KEY STAKEHOLDERS	Project Sponsor: Educational Institution Management / Project Manager: Harshad Dhokane / Development Team: UI/UX Designers, Frontend and Backend Developers / QA Team: Responsible for functional and security testing / End Users: Students, Teachers, and Administrative Staff

Prepared By:	Harshad Dhokane	Senior Project Manager	Date: 31/03/2025

## MILESTONES
TASK BREAKDOWN AND MILESTONES
Phase 1: Planning & Requirements
Duration: 7 days (31/03/2025 – 07/04/2025)
Task ID	Task Name	Duration	Dependencies
1.1	Identify Stakeholders	2 days	None
1.2	Define Functional Specifications	3 days	1.1
1.3	Finalize Project Plan	2 days	1.2

Milestone 1: Project Plan Approved (07/04/2025)

Phase 2: UI/UX Design
Duration: 14 days (08/04/2025 – 21/04/2025)
Task ID	Task Name	Duration	Dependencies
2.1	Create Wireframes	5 days	1.3
2.2	Review and Approve Wireframes	2 days	2.1
2.3	Create Visual Designs	5 days	2.2
2.4	UI/UX Design Sign-Off	2 days	2.3

Milestone 2: UI/UX Design Approval (21/04/2025)

Phase 3: Backend Development
Duration: 15 days (22/04/2025 – 12/05/2025)
Task ID	Task Name	Duration	Dependencies
3.1	Database Setup	5 days	2.4
3.2	Develop Authentication System	7 days	3.1
3.3	Backend API Development	3 days	3.2

Milestone 3: Backend Development Complete (12/05/2025)

Phase 4: Frontend Development
Duration: 10 days (13/05/2025 – 28/05/2025)
Task ID	Task Name	Duration	Dependencies
4.1	Homepage Implementation	4 days	3.3
4.2	Student Portal Development	4 days	4.1
4.3	Teacher Portal Development	2 days	4.2

Milestone 4: Frontend Integration Complete (28/05/2025)

Phase 5: Testing & Debugging
Duration: 7 days (29/05/2025 – 07/06/2025)
Task ID	Task Name	Duration	Dependencies
5.1	Functional Testing	4 days	4.3
5.2	Security and Performance Testing	3 days	5.1

Milestone 5: Testing Phase Complete (07/06/2025)

Phase 6: Final Deployment & Training
Duration: 8 days (08/06/2025 – 15/06/2025)
Task ID	Task Name	Duration	Dependencies
6.1	Deploy Website to Production	3 days	5.2
6.2	User Training and Documentation	5 days	6.1

Milestone 6: Project Completion and Handover (15/06/2025)

## QUALITY REQUIREMENTS AND STANDARDS
QUALITY REQUIREMENTS AND STANDARDS
ID	Requirement/Standard	Description	Acceptance Criteria
Q1	User Interface (UI)	Intuitive, easy-to-use, and responsive interface for students and teachers.	95% positive user feedback post-launch.
Q2	Performance	Load time for all pages should be ≤ 3 seconds.	Response time under 3 seconds for 95% of requests.
Q3	Security	Encrypted communication using SSL, secure login using password hashing.	Penetration test success rate of 99%.
Q4	Cross-Browser Compatibility	Full functionality on Chrome, Firefox, Safari, and Edge.	100% cross-browser functionality validated.
Q5	Mobile Responsiveness	Seamless viewing and interaction on all devices.	Pass mobile-friendly test with 90%+ score.
Q6	Authentication and Authorization	Role-based access with separate portals for students and teachers.	100% role-based access with no errors.
Q7	Functional Accuracy	Ensure all defined features work as intended.	100% test cases pass in functional testing.
Q8	Scalability	Support concurrent user traffic of 500+ users.	Load test with 500 concurrent users.
Q9	Backup and Recovery	Implement automatic data backup with disaster recovery measures.	Recovery time ≤ 1 hour.
Q10	Compliance	Compliance with GDPR and other applicable regulations.	Audit report showing 100% compliance.

## MEASUREMENT PLAN(QUALITY CONTROL AND VALIDATION)
MEASUREMENT PLAN (QUALITY CONTROL AND VALIDATION)
Metric	Target	Measurement Method	Frequency	Responsible Team
UI/UX Satisfaction	95% positive feedback	Post-launch survey	End of project	QA & UI/UX Team
Page Load Speed	≤ 3 seconds per page	Performance Testing Tools	Weekly	Backend Team
Security Audit Score	99% penetration success	Security Audit & Pen Test	Bi-Monthly	Security Analyst
Cross-Browser Testing	100% cross-browser support	Manual and Automated Testing	End of UI phase	QA Team
Functional Accuracy	100% test pass rate	Functional Test Reports	Weekly	QA Team
Uptime & Availability	≥ 99.9% uptime	Monitoring System	Daily	IT Operations
Authentication Logs	No unauthorized access	Security Monitoring	Real-time	Security Team
Backup & Recovery Time	≤ 1 hour	Backup & Recovery Simulation	Monthly	IT Support Team

## RESPONSIBILITY ASSIGNMENT MATRIX
RESPONSIBILITY ASSIGNMENT MATRIX (RAM)
The RACI matrix assigns roles and responsibilities for each task based on:

R: Responsible (Directly performs the task)
A: Accountable (Has final authority and approval)
C: Consulted (Provides input or expertise)
I: Informed (Kept in the loop on task progress)

RESPONSIBILITY ASSIGNMENT MATRIX
Task Name	Project Manager	UI/UX Designer	Backend Developer	Frontend Developer	QA Team	IT Support
Identify Stakeholders	A	C	I	I	I	I
Define Functional Specs	R	C	C	I	I	I
Finalize Project Plan	A	I	I	I	I	I
Create Wireframes	I	R	I	I	I	I
Review and Approve Wireframes	A	C	I	I	I	I
Create Visual Designs	I	R	I	I	I	I
UI/UX Design Sign-Off	A	I	I	I	I	I
Database Setup	I	I	R	I	I	I
Develop Authentication System	I	I	R	I	I	I
Backend API Development	I	I	R	I	I	I
Homepage Implementation	I	I	I	R	I	I
Student Portal Development	I	I	I	R	I	I
Teacher Portal Development	I	I	I	R	I	I
Functional Testing	I	I	I	I	R	I
Security and Performance Testing	I	I	I	I	R	I
Deploy Website to Production	I	I	I	I	I	R
User Training and Documentation	I	I	I	I	R	C

## GANTT CHART AND RESOURCE
	Name	Duration		Predecessor	Resource person
	1 Class Website Development	30 days			Project Manager
	1.1 Planning & Requirements	5 days			Project Manager;Business Analyst
	1.1.1 Identify Stakeholders	1 day			Business Analyst;Project Manager
	1.1.2 Define Functional Specs	2 days			Business Analyst
	1.1.3 Approve Requirements	2 days		4	Client/Stakeholders
	MILESTONE			5
	1.2 UI/UX Design	7 days		5	UI/UX Designer
	1.2.1 Create Wireframes	3 days		5	UI/UX Designer
	1.2.2 Design Mockups	3 days		8	UI/UX Designer
	1.2.3 Get Design Approval	1 day		9	Client/Stakeholders
	MILESTONE			10
	1.3 Backend Development	8 days		10;5	Backend Developer
	1.3.1 Database Setup	3 days		10	Backend Developer
	1.3.2 Develop Authentication	2 days		13	Backend Developer
	1.3.3 Implement Server Logic	3 days		14;10	Backend Developer
	MILESTONE			15
	1.4 Frontend Development	6 days		15	Frontend Developer
	1.4.1 Homepage Development	2 days		15	Frontend Developer
	1.4.2 Student Portal Development	2 days		18	Frontend Developer
	1.4.3 Teacher Portal Development	2 days		18	Frontend Developer
	MILESTONE			20
	1.5 Integration & Testing	5 days		20;15	QA Engineer
	1.5.1 Functional Testing	2 days		20	QA Engineer
	1.5.2 Security & Load Testing	2 days		23	QA Engineer
	1.5.3 Bug Fixes	1 day		24	Backend Developer;Frontend Developer
	MILESTONE			25
	1.6 Deployment & Launch	4 days		25	System Administrator
	1.6.1 Deploy Website	1 day		25	System Administrator
	1.6.2 Final Review & Approval	2 days		28	Client/Stakeholders
	1.6.3 Launch Website	1 day		29	System Administrator

NAME	NAME	RBS		TYPE	MAX	E-MAIL	material label	Initils	group	std rate	overtime rate	cost per use	accure at	base calender
Project Manager	Project Manager	Overall project supervision		Work	2.5	100		P		100/hour	54/hour	100	Prorated	Standard
Business Analyst	Business Analyst	Requirements gathering, approvals		Work	2.5	100		B		80/hour	654/hour	100	Prorated	Standard
UI/UX Designer	UI/UX Designer	Wireframes, mockups, design approval		Work	2	100		U		50/hour	0/hour	50	Prorated	Standard
Backend Developer	Backend Developer	Server logic, database setup		Work	2	100		B		50/hour	0/hour	90	Prorated	Standard
Frontend Developer	Frontend Developer	UI implementation, portals		Work	3	100		F		60/hour	0/hour	45	Prorated	Standard
QA Engineer	QA Engineer	Functional, security, and load testing		Work	2	100		Q		60/hour	0/hour	21	Prorated	Standard
System Administrator	System Administrator	Website deployment and configuration		Work	2	100		S		80/hour	0/hour	231	Prorated	Standard
Client/Stakeholders	Client/Stakeholders	Review, approval, and feedback		Work	1	100		C		70/hour	0/hour	534	Prorated	Standard