## PROJECT CHARTER
PROJECT CHARTER
PROJECT NAME |  |  | PROJECT MANAGER | PROJECT SPONSOR
Development of a Class Website |  |  | Jane Matthews | Jill DeGrassio
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
jane.matthews@positivecharge.com |  | 9086745645 | Web Development, IT Operations, and Project Management
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE | EXPECTED COMPLETION DATE
Wendy Williams (Web Development) |  |  | 22/01/2025 | 25/07/2025
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS | ESTIMATED COSTS
Rakesh Agarwal (Director of IT Operations) |  |  | 15000 | 250000
PROJECT OVERVIEW
PROBLEM OR ISSUE | The goal of this project is to develop a custom class website with features such as a home page, syllabus page, student and teacher login portals, and other relevant sections to improve communication and learning management.
PURPOSE OF PROJECT | The implementation of this custom class website will enhance the educational experience by providing a centralized platform for students and teachers to access critical resources. It aims to simplify communication, facilitate efficient information sharing, and promote user-friendly engagement.
BUSINESS CASE | Educational institutions are increasingly relying on digital platforms to improve teaching and learning. A custom-built class website will cater to specific class needs, ensure a unique identity, and avoid dependency on third-party solutions. This initiative will provide a streamlined user experience for students and teachers and reduce administrative overhead.
GOALS / METRICS | The project goal is to design and implement a fully functional class website by the target date. Metrics for success include meeting deadlines, maintaining website uptime of 99%, achieving a 95% satisfaction rate in user feedback, and ensuring compatibility with all major devices and browsers.
EXPECTED DELIVERABLES | - A responsive class website with: 1. Home page 2. Syllabus page 3. Student login portal 4. Teacher login portal 5. Announcements and updates section 6. Contact and helpdesk page - Documentation for website management and maintenance.
PROJECT SCOPE
WITHIN SCOPE | Design and development of a custom website template. Integration of login portals for students and teachers. Development of a content management system for syllabus and announcements. User testing and feedback incorporation. Providing training for teachers to manage the website content.
OUTSIDE OF SCOPE | Hosting and domain registration (to be handled by the institution). Third-party API integrations for external learning tools. Maintenance and updates post-deployment.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START | FINISH
Form Project Team / Preliminary Review / Scope |  |  | 22/01/2025 | 31/01/2025
Finalize Project Plan / Charter / Kick Off |  |  | 2025-01-02 | 15/02/2025
Define Phase |  |  | 16/02/2025 | 28/02/2025
UI/UX Design Phase |  |  | 2025-01-03 | 15/03/2025
Backend Development |  |  | 16/03/2025 | 15/05/2025
Frontend Integration |  |  | 16/05/2025 | 15/06/2025
Testing Phase |  |  | 16/06/2025 | 2025-10-07
Project Summary Report and Close Out |  |  | 2025-11-07 | 25/07/2025
RESOURCES
PROJECT TEAM | Janine Remagio |  | Project Manager
| David Coen |  | Lead Developer
| Rita Preze |  | UI/UX Designer
| Lisa Jones |  | QA Specialist
| Donald Smythe |  | Frontend Developer
SUPPORT RESOURCES | IT Operations, Sales, and Web Development Team
SPECIAL NEEDS | Access to existing class data, user feedback, and testing environments.
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | AMOUNT
Labor | Lead Developer |  | 150000
Labor | UI/UX Designer |  | 70000
Labor | QA Specialist |  | 25000
Miscellaneous | Third-Party Software |  | 5000
| TOTAL COSTS |  | 250000
BENEFITS AND CUSTOMERS
PROCESS OWNER | Jane Matthews - Project Manager
KEY STAKEHOLDERS | Jill DeGrassio, Teachers, Students
FINAL CUSTOMER | Students and teachers utilizing the class website.
EXPECTED BENEFITS | The class website will streamline communication between students and teachers, reduce administrative tasks, and provide a professional and engaging user experience. It will also facilitate efficient syllabus and announcement sharing, enhancing overall satisfaction.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  | ESTIMATED BENEFIT AMOUNT
Improved Communication | IT and Management Estimations |  |  | 10000
Enhanced User Satisfaction | User Surveys |  |  | 8000
Reduced Administrative Work | Operations' Estimations |  |  | 5000
Cost Savings on Third-Party | Software Estimations |  |  | 2000
TOTAL BENEFIT |  |  |  | 25000
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | - Delays in obtaining feedback from students and teachers during the testing phase. - Potential compatibility issues with older devices and browsers. - Limited access to IT resources during peak institutional periods.
CONSTRAINTS | - Project timeline is tight due to the academic calendar. - Team members may need to multitask with other institutional IT priorities.
ASSUMPTIONS | - Necessary approvals from stakeholders will be obtained on time. - Required class data and content for the website will be provided promptly.
PREPARED BY | TITLE |  |  | DATE
Jane Matthews | Senior Project Manager |  |  | 21/01/2025

## PROJECT MANAGEMENT PLAN
PROJECT MANAGEMENT PLAN
OVERVIEW
Purpose | Develop a class website including home page, syllabus, student and teacher login portals.
Scope | Comprehensive design, secure login, usability focus.
Objective | Deliver within 6 months, $250,000 budget.
Assumptions | Content provided by stakeholders.
Constraints | Timeline and budget limitations, cross-browser/device compatibility.
Project Deliverables | Fully functional class website, documentation, secure portals for students and teachers.
Schedule | Start Date: January 22, 2025, | End Date: July 25, 2025,
Budget | 250000
Evolution of the Plan | Plan updated at each milestone for scope, schedule, and resources.
PROJECT ORGANIZATION
External Interfaces | Coordinate with educators and students; IT for infrastructure support.
Internal Structure | Roles | Responsibility
| Project Manager | Oversee project lifecycle, monitor progress, and manage risks.
| Web Developers | Design, code, and implement website functionality.
| UI/UX Designer | Develop wireframes, design mockups, and ensure responsive design.
| Backend Developer | Set up database, develop authentication, and integrate backend logic.
| Frontend Developer | Implement front-end components, including portals and pages.
| QA Specialist | Conduct functionality, security, and usability testing.
| System Administrator | Deploy and manage the server and infrastructure.
Roles and Responsibilities | Assign roles and responsibilities to team members, ensuring clear ownership of tasks.
MANAGERIAL PROCESS PLAN
Start-Up Plans | Conduct resource estimation and plan staffing. Acquire required tools and technologies. Provide training on CMS, security protocols, and responsive design.
Work Plan | Phase 1: Requirements Gathering & Planning Phase 2: UI/UX Design Phase 3: Backend & Frontend Development Phase 4: Integration & Testing Phase 5: Deployment & Training
Control Plan | Conduct weekly progress meetings to track progress and address deviations. Monitor deliverables and adjust timelines if required. Regularly update the project charter and Gantt chart.
Risk Management Plan | Identified Risks: Delays in stakeholder feedback. Compatibility issues across devices. Resource unavailability during critical phases. Mitigation Strategies: Maintain buffer time for feedback loops. Conduct cross-device testing during development. Pre-schedule resource availability.
Closeout Plan | Finalize website functionalities and documentation. Conduct user training and collect feedback. Conduct a retrospective to document lessons learned.
TECHNICAL PROCESS PLAN
Process Model | Follow Agile model for iterative development and progress tracking.
Methods, Tools, and Techniques | Tools | HTML, CSS, JavaScript for frontend. CMS for content management. Git for version control.
| Techniques | Responsive design for multi-device compatibility. Usability optimization and secure login.
Infrastructure Plan | Hosting Services: Set up a secure hosting environment with backups. Security: Implement SSL certificates and access control mechanisms.
Product Acceptance Plan | Conduct user testing with students and teachers. Validate functionality against acceptance criteria. Obtain formal acceptance from key stakeholders.
SUPPORTING PROCESS PLAN
Configuration Management Plan | Version control using Git for source code management.
Verification and Validation Plan | Functional, performance, and user acceptance testing.
Documentation Plan | User manuals and technical documentation.
Quality Assurance Plan | Adhere to quality standards through code reviews and QA processes.
Reviews and Audits | Bi-weekly reviews with stakeholders to ensure alignment.
Problem Resolution Plan | Log and resolve issues efficiently using an issue tracker.
Subcontractor Management Plan | No subcontractors planned for this project.
Process Improvement Plan | Integrate feedback continuously for process improvement.

## REQUIREMENT MATRIX
REQUIREMENT TRACEABILITY MATRIX (RTM)
PROJECT NAME: Class Website Development
DATE: March 31, 2025
Prepared By: Harshad Dhokane
Requirement Traceability Matrix (RTM)
Requirement ID | Requirement Description | Category | Source/Stakeholder | Priority | WBS Code | Deliverable | Verification Method
R1 | Define project scope and requirements | Business Requirement | Project Manager, Educators | High | 1.1 | Approved Scope Document | Stakeholder Approval
R2 | Identify key stakeholders and gather inputs | Business Requirement | Project Manager | High | 1.1.1 | Stakeholder Input Report | Meeting Records
R3 | Define functional and non-functional specs | Functional Requirement | Educators, Students | High | 1.1.2 | Functional Requirements Document | Review and Sign-Off
R4 | Create wireframes for website layout | UI/UX Design | UI/UX Designer | Medium | 1.2.1 | Initial Wireframes | UI/UX Review
R5 | Develop UI mockups for all pages | UI/UX Design | UI/UX Designer | Medium | 1.2.2 | Final Visual Designs | Design Approval
R6 | Set up the database and relationships | Technical | Database Administrator | High | 1.3.1 | Database Schema Design | Database Review
R7 | Develop student and teacher authentication | Technical | Backend Developer | High | 1.3.2 | Secure Authentication System | Unit Testing
R8 | Code and implement homepage layout | Development | Frontend Developer | High | 1.4.1 | Homepage Implementation | Code Review
R9 | Develop student login and dashboard | Development | Frontend Developer | High | 1.4.2 | Student Portal Implementation | Functional Testing
R10 | Conduct functional and performance testing | Quality Assurance | QA Team | High | 1.5.1 | Test Report | Test Case Results
R11 | Deploy the website to a secure server | Deployment | System Administrator | High | 1.5.2 | Live Website Deployment | Deployment Verification
R12 | Create user manuals and technical documentation | Documentation | Project Manager | Medium | 1.6 | User Manual and Admin Guide | Documentation Review
R13 | Obtain feedback from users and incorporate improvements | User Feedback | Students, Teachers | Medium | 1.7 | Feedback Report | Survey Analysis
R14 | Provide training for managing website content | Training | Project Manager, IT | Medium | 1.8 | Training Sessions and Guides | Training Feedback
Traceability Mapping Summary:
High Priority: Critical functionality including scope definition, authentication, homepage, portals, and database setup.
Medium Priority: UI/UX wireframes, documentation, feedback collection, and content management training.
Verification and Validation Methods
Stakeholder Approval: Scope documents and functional requirements sign-off.
UI/UX Reviews: Visual design and wireframe validation.
Code Reviews: Verify backend and frontend implementation.
Testing: Unit testing, functional testing, and performance validation.
Training Feedback: Evaluation from training sessions to ensure knowledge transfer.
Prepared By:
Harshad Dhokane
Senior Project Manager
Date: 31/03/2025

## SCOPE STATEMENT
PROJECT SCOPE STATEMENT FOR CLASS WEBSITE DEVELOPMENT
PROJECT NAME | CLASS WEBSITE DEVELOPMENT
DATE | 2025-03-31
PREPARED BY | HARSHAD DHOKANE
PROJECT SCOPE STATEMENT
PROJECT OBJECTIVE | The objective of this project is to design, develop, and deploy a fully functional class website that includes a home page, syllabus page, student and teacher login portals, announcements section, and contact/helpdesk page. The project will be completed within 3 months and within the allocated budget of $50,000.00.
PROJECT SCOPE DESCRIPTION | The class website will: Include essential features: Homepage with key information. Syllabus page displaying course outlines and updates. Secure student and teacher login portals. Announcement and updates section to inform users of changes. Contact/helpdesk page for queries and technical support. Offer an intuitive UI/UX design for ease of use. Ensure compatibility across multiple devices and browsers. Implement secure authentication mechanisms to protect user data.
DELIVERABLES | The following deliverables will be produced: Fully functional, responsive class website. Secure login portals for students and teachers. UI/UX wireframes and mockups. Database for managing website content and user data. User and technical documentation for website management. Training sessions and guides for content management.
IN-SCOPE ITEMS | Design and Development: | UI/UX wireframes and interface designs. Frontend and backend development. Integration of login and content management system.
| Testing and Deployment: | Functional, performance, and security testing. Hosting and deployment on a secure server.
| Documentation and Training: | Creation of user manuals and training resources. Conducting training sessions for educators to manage content.
OUT-OF-SCOPE ITEMS | Hosting and Domain Registration: Institution is responsible for acquiring the domain and hosting. Third-party Integrations: External learning tools and APIs are not included. Ongoing Maintenance and Updates: Post-deployment support is not part of this phase.
PROJECT TIMELINE | Phase | Start Date | End Date
| Planning & Requirements | 31/03/2025 | 2025-07-04
| UI/UX Design | 2025-08-04 | 21/04/2025
| Backend Development | 22/04/2025 | 2025-12-05
| Frontend Development | 13/05/2025 | 28/05/2025
| Testing & Debugging | 29/05/2025 | 2025-07-06
| Final Deployment & Training | 2025-08-06 | 15/06/2025
ESTIMATED COST | The project is expected to be delivered within a budget of: $50,000.00
RISKS AND CONSTRAINTS | Risks: | Delays in stakeholder feedback during testing. Technical challenges with ensuring multi-device compatibility. Resource unavailability due to competing institutional priorities.
| Constraints: | Strict timeline due to academic schedule. Budgetary limits and availability of key team members.
ASSUMPTIONS | Necessary approvals and feedback will be provided on time. Content (syllabus, announcements) will be delivered by stakeholders. IT infrastructure will be available for deployment and security testing.
KEY STAKEHOLDERS | Project Sponsor: Educational Institution Management Project Manager: Harshad Dhokane Development Team: UI/UX Designers, Frontend and Backend Developers QA Team: Responsible for functional and security testing End Users: Students, Teachers, and Administrative Staff
Prepared By: | Harshad Dhokane | Senior Project Manager | Date: 31/03/2025

## MILESTONES
TASK BREAKDOWN AND MILESTONES
Phase 1: Planning & Requirements
Duration: 7 days (31/03/2025 – 07/04/2025)
Task ID | Task Name | Duration | Dependencies
1.1 | Identify Stakeholders | 2 days | None
1.2 | Define Functional Specifications | 3 days | 1.1
1.3 | Finalize Project Plan | 2 days | 1.2
Milestone 1: Project Plan Approved (07/04/2025)
Phase 2: UI/UX Design
Duration: 14 days (08/04/2025 – 21/04/2025)
Task ID | Task Name | Duration | Dependencies
2.1 | Create Wireframes | 5 days | 1.3
2.2 | Review and Approve Wireframes | 2 days | 2.1
2.3 | Create Visual Designs | 5 days | 2.2
2.4 | UI/UX Design Sign-Off | 2 days | 2.3
Milestone 2: UI/UX Design Approval (21/04/2025)
Phase 3: Backend Development
Duration: 15 days (22/04/2025 – 12/05/2025)
Task ID | Task Name | Duration | Dependencies
3.1 | Database Setup | 5 days | 2.4
3.2 | Develop Authentication System | 7 days | 3.1
3.3 | Backend API Development | 3 days | 3.2
Milestone 3: Backend Development Complete (12/05/2025)
Phase 4: Frontend Development
Duration: 10 days (13/05/2025 – 28/05/2025)
Task ID | Task Name | Duration | Dependencies
4.1 | Homepage Implementation | 4 days | 3.3
4.2 | Student Portal Development | 4 days | 4.1
4.3 | Teacher Portal Development | 2 days | 4.2
Milestone 4: Frontend Integration Complete (28/05/2025)
Phase 5: Testing & Debugging
Duration: 7 days (29/05/2025 – 07/06/2025)
Task ID | Task Name | Duration | Dependencies
5.1 | Functional Testing | 4 days | 4.3
5.2 | Security and Performance Testing | 3 days | 5.1
Milestone 5: Testing Phase Complete (07/06/2025)
Phase 6: Final Deployment & Training
Duration: 8 days (08/06/2025 – 15/06/2025)
Task ID | Task Name | Duration | Dependencies
6.1 | Deploy Website to Production | 3 days | 5.2
6.2 | User Training and Documentation | 5 days | 6.1
Milestone 6: Project Completion and Handover (15/06/2025)

## QUALITY REQUIREMENTS AND STANDA
QUALITY REQUIREMENTS AND STANDARDS
ID | Requirement/Standard | Description | Acceptance Criteria
Q1 | User Interface (UI) | Intuitive, easy-to-use, and responsive interface for students and teachers. | 95% positive user feedback post-launch.
Q2 | Performance | Load time for all pages should be ≤ 3 seconds. | Response time under 3 seconds for 95% of requests.
Q3 | Security | Encrypted communication using SSL, secure login using password hashing. | Penetration test success rate of 99%.
Q4 | Cross-Browser Compatibility | Full functionality on Chrome, Firefox, Safari, and Edge. | 100% cross-browser functionality validated.
Q5 | Mobile Responsiveness | Seamless viewing and interaction on all devices. | Pass mobile-friendly test with 90%+ score.
Q6 | Authentication and Authorization | Role-based access with separate portals for students and teachers. | 100% role-based access with no errors.
Q7 | Functional Accuracy | Ensure all defined features work as intended. | 100% test cases pass in functional testing.
Q8 | Scalability | Support concurrent user traffic of 500+ users. | Load test with 500 concurrent users.
Q9 | Backup and Recovery | Implement automatic data backup with disaster recovery measures. | Recovery time ≤ 1 hour.
Q10 | Compliance | Compliance with GDPR and other applicable regulations. | Audit report showing 100% compliance.

## MEASUREMENT PLAN(QUALITY CONTRO
MEASUREMENT PLAN (QUALITY CONTROL AND VALIDATION)
Metric | Target | Measurement Method | Frequency | Responsible Team
UI/UX Satisfaction | 95% positive feedback | Post-launch survey | End of project | QA & UI/UX Team
Page Load Speed | ≤ 3 seconds per page | Performance Testing Tools | Weekly | Backend Team
Security Audit Score | 99% penetration success | Security Audit & Pen Test | Bi-Monthly | Security Analyst
Cross-Browser Testing | 100% cross-browser support | Manual and Automated Testing | End of UI phase | QA Team
Functional Accuracy | 100% test pass rate | Functional Test Reports | Weekly | QA Team
Uptime & Availability | ≥ 99.9% uptime | Monitoring System | Daily | IT Operations
Authentication Logs | No unauthorized access | Security Monitoring | Real-time | Security Team
Backup & Recovery Time | ≤ 1 hour | Backup & Recovery Simulation | Monthly | IT Support Team

## RESPONSIBILITY ASSIGNMENT MATRI
RESPONSIBILITY ASSIGNMENT MATRIX (RAM)
The RACI matrix assigns roles and responsibilities for each task based on:
R: Responsible (Directly performs the task)
A: Accountable (Has final authority and approval)
C: Consulted (Provides input or expertise)
I: Informed (Kept in the loop on task progress)
RESPONSIBILITY ASSIGNMENT MATRIX
Task Name | Project Manager | UI/UX Designer | Backend Developer | Frontend Developer | QA Team | IT Support
Identify Stakeholders | A | C | I | I | I | I
Define Functional Specs | R | C | C | I | I | I
Finalize Project Plan | A | I | I | I | I | I
Create Wireframes | I | R | I | I | I | I
Review and Approve Wireframes | A | C | I | I | I | I
Create Visual Designs | I | R | I | I | I | I
UI/UX Design Sign-Off | A | I | I | I | I | I
Database Setup | I | I | R | I | I | I
Develop Authentication System | I | I | R | I | I | I
Backend API Development | I | I | R | I | I | I
Homepage Implementation | I | I | I | R | I | I
Student Portal Development | I | I | I | R | I | I
Teacher Portal Development | I | I | I | R | I | I
Functional Testing | I | I | I | I | R | I
Security and Performance Testing | I | I | I | I | R | I
Deploy Website to Production | I | I | I | I | I | R
User Training and Documentation | I | I | I | I | R | C

## GANTT CHART AND RESOURCE
| Name | Duration | Predecessor | Resource person
| 1 Class Website Development | 30 days |  | Project Manager
| 1.1 Planning & Requirements | 5 days |  | Project Manager;Business Analyst
| 1.1.1 Identify Stakeholders | 1 day |  | Business Analyst;Project Manager
| 1.1.2 Define Functional Specs | 2 days |  | Business Analyst
| 1.1.3 Approve Requirements | 2 days | 4 | Client/Stakeholders
| MILESTONE |  | 5
| 1.2 UI/UX Design | 7 days | 5 | UI/UX Designer
| 1.2.1 Create Wireframes | 3 days | 5 | UI/UX Designer
| 1.2.2 Design Mockups | 3 days | 8 | UI/UX Designer
| 1.2.3 Get Design Approval | 1 day | 9 | Client/Stakeholders
| MILESTONE |  | 10
| 1.3 Backend Development | 8 days | 10;5 | Backend Developer
| 1.3.1 Database Setup | 3 days | 10 | Backend Developer
| 1.3.2 Develop Authentication | 2 days | 13 | Backend Developer
| 1.3.3 Implement Server Logic | 3 days | 14;10 | Backend Developer
| MILESTONE |  | 15
| 1.4 Frontend Development | 6 days | 15 | Frontend Developer
| 1.4.1 Homepage Development | 2 days | 15 | Frontend Developer
| 1.4.2 Student Portal Development | 2 days | 18 | Frontend Developer
| 1.4.3 Teacher Portal Development | 2 days | 18 | Frontend Developer
| MILESTONE |  | 20
| 1.5 Integration & Testing | 5 days | 20;15 | QA Engineer
| 1.5.1 Functional Testing | 2 days | 20 | QA Engineer
| 1.5.2 Security & Load Testing | 2 days | 23 | QA Engineer
| 1.5.3 Bug Fixes | 1 day | 24 | Backend Developer;Frontend Developer
| MILESTONE |  | 25
| 1.6 Deployment & Launch | 4 days | 25 | System Administrator
| 1.6.1 Deploy Website | 1 day | 25 | System Administrator
| 1.6.2 Final Review & Approval | 2 days | 28 | Client/Stakeholders
| 1.6.3 Launch Website | 1 day | 29 | System Administrator
NAME | NAME | RBS | TYPE | MAX | E-MAIL | material label | Initils | group | std rate | overtime rate | cost per use | accure at | base calender
Project Manager | Project Manager | Overall project supervision | Work | 2.5 | 100 |  | P |  | 100/hour | 54/hour | 100 | Prorated | Standard
Business Analyst | Business Analyst | Requirements gathering, approvals | Work | 2.5 | 100 |  | B |  | 80/hour | 654/hour | 100 | Prorated | Standard
UI/UX Designer | UI/UX Designer | Wireframes, mockups, design approval | Work | 2 | 100 |  | U |  | 50/hour | 0/hour | 50 | Prorated | Standard
Backend Developer | Backend Developer | Server logic, database setup | Work | 2 | 100 |  | B |  | 50/hour | 0/hour | 90 | Prorated | Standard
Frontend Developer | Frontend Developer | UI implementation, portals | Work | 3 | 100 |  | F |  | 60/hour | 0/hour | 45 | Prorated | Standard
QA Engineer | QA Engineer | Functional, security, and load testing | Work | 2 | 100 |  | Q |  | 60/hour | 0/hour | 21 | Prorated | Standard
System Administrator | System Administrator | Website deployment and configuration | Work | 2 | 100 |  | S |  | 80/hour | 0/hour | 231 | Prorated | Standard
Client/Stakeholders | Client/Stakeholders | Review, approval, and feedback | Work | 1 | 100 |  | C |  | 70/hour | 0/hour | 534 | Prorated | Standard